# ECE 416 Updated Project Description and Schedule

Proposed revision based on project progress through March 13, 2026

| Date | March 13, 2026 | Project # | 15 |
| --- | --- | --- | --- |
| Project title | JamGuard: Portable Anti-Jam GNSS Receiver |  |  |

# Updated project description

JamGuard is now best described as a portable multi-antenna anti-jam GNSS prototype rather than a shoe-integrated wearable product. The current design centers on a 5-channel coherent KrakenSDR front end, a Raspberry Pi 5 for host control, logging, UI, and orchestration, and a PolarFire SoC RISC-V FPGA platform intended to become a major compute element for real-time beamforming, filtering, and interference-mitigation tasks once coherent array data is validated. This framing preserves innovation while keeping the implementation sequence realistic: first establish a stable physical array and coherent data path, then move the most timing-critical or parallel signal-processing functions onto the FPGA/RISC-V platform.

## Recommended replacement for the “Work performed since approval of the proposal in ECE 414” section

• The project scope was narrowed from a wearable shoe-focused navigation concept to a more achievable one-person portable anti-jam GNSS prototype.

• A hybrid architecture was selected in which KrakenSDR provides coherent multi-channel RF data, the Raspberry Pi 5 serves mainly as the system host for orchestration, logging, UI, and test control, and the PolarFire SoC Discovery Kit is intended to carry a large share of the beamforming and other low-latency signal-processing workload because those tasks better match FPGA parallelism and deterministic dataflow.

• Major hardware selection and procurement were largely completed, with emphasis placed on KrakenSDR, Raspberry Pi 5, PolarFire SoC, GNSS antennas, coaxial cabling, and first-prototype mechanical mounting hardware.

• Raspberry Pi 5 and KrakenSDR software bring-up were completed successfully. The official KrakenRF Raspberry Pi 5 image was installed, the KrakenSDR hardware was detected, the web interface was brought up, and the data-acquisition pipeline was verified as alive.

• System health indicators including connection, frame synchronization, sample-delay synchronization, IQ synchronization, and power checks were verified as acceptable during bring-up, indicating that the base platform is working before array integration.

• Mechanical planning for the first physical 5-antenna array is now underway, with focus on a rigid prototype geometry, aluminum ground-plane implementation, repeatable antenna spacing, and clean cabling/strain relief.

• To reduce risk, the project will phase FPGA integration carefully: a stable baseline array and reference processing path should be established first, but the FPGA/RISC-V remains a central target rather than an optional add-on. Optional AI logic and nonessential sensors are still treated as later integration or stretch items compared with core FPGA beamforming, filtering, and control integration.

# Recommended edits to the parts and components section

The current component list should be reorganized around what is confirmed core, what is in active integration, and what is optional or deferred. This makes the report match actual progress, reduces scope creep, and more clearly shows that the PolarFire SoC is part of the core compute architecture rather than a peripheral future add-on.

| Subsystem | Part / item | Role | Recommended status | Edit note |
| --- | --- | --- | --- | --- |
| Host compute | Raspberry Pi 5 starter kit | System host for orchestration, logging, UI, networking, and higher-level software control | Confirmed working | Keep in core path; this is already operational. |
| RF front end | KrakenSDR | 5-channel coherent SDR front end | Confirmed working | Keep in core path; software bring-up already completed. |
| FPGA / RISC-V | PolarFire SoC Discovery Kit | Primary acceleration platform for beamforming, filtering, and low-latency signal processing, with RISC-V supervisory/control capability | Core high-priority integration | Present as a central compute element after baseline array validation, not as a stretch add-on. |
| Antenna array | 5x active GNSS L1/L2 patch antennas | Array inputs for coherent capture and beamforming | In integration | This is the immediate bottleneck and should be highlighted. |
| RF cabling | U.FL-to-SMA and SMA-to-SMA coax cables | Connect each antenna to KrakenSDR | In integration | Keep only the cable set actually required for prototype 1. |
| Mechanical prototype | Rigid plate / ground plane, standoffs, strain relief | Repeatable first 5-antenna array build | In progress | Move this higher in the list because it is now critical. |
| RF validation tools | L1 filter, attenuators, terminators, SMA adapters | Controlled testing and protection | Useful support items | Keep, but describe them as test infrastructure rather than the core build. |
| Backup host | Orange Pi 5 Pro | Fallback compute platform | Optional / deferred | Demote to optional because Raspberry Pi 5 is already working. |
| Shielding | Ramsey shield box / contained-test items | Improved controlled RF testing | Optional but beneficial | Keep as a lab-quality improvement item. |
| Stretch items | IMU, buzzer, haptic motor, splitter/coupler extras | Additional features | Deferred | Move to an optional/deferred subsection to avoid inflating scope. |

# Recommended schedule revision

The schedule should now distinguish completed bring-up tasks from remaining integration tasks. The immediate critical path is antenna-array assembly -> coherent capture validation -> calibration and beamforming partitioning -> FPGA offload/integration -> controlled interference testing -> final end-to-end demo.

| Aim / milestone | Revised target | Status as of Mar. 13 | Reason for the change |
| --- | --- | --- | --- |
| Aim 1: Core platform bring-up and first array prototype | Late Mar. | In progress | Extend aim through array build and first coherent captures. |
| Aim 1.1: Freeze updated architecture, parts list, and wiring plan | Completed | Done | Architecture and wiring are already defined well enough to proceed. |
| Aim 1.2: Bring up Raspberry Pi 5 host, OS, networking, and logging | Completed | Done | Pi 5 host is already operational. |
| Aim 1.3: Bring up KrakenSDR and verify stable streaming / web UI | Completed | Done | KrakenSDR bring-up and base DAQ health were verified. |
| Aim 1.4: Build first rigid 5-antenna prototype with ground plane and strain relief | Late Mar. | Active next task | This is now the main hardware bottleneck. |
| Aim 1.5: Record first coherent captures and verify channel health, phase behavior, and geometry | Late Mar. / Early Apr. | Pending | This closes baseline platform validation after array assembly. |
| Aim 2: Calibration, beamforming partitioning, and FPGA integration | Mid- to late Apr. | Next phase | More realistic after first usable coherent data is available, while keeping FPGA integration central. |
| Aim 2.1: Implement logging and channel-calibration checks | Early Apr. | Pending | Calibration begins after first valid captures exist. |
| Aim 2.2: Establish reference delay-and-sum / MVDR flow and partition tasks between host and FPGA | Early Apr. | Pending | Create a verified reference chain, then identify what should move to the PolarFire SoC. |

## Recommended schedule revision (continued)

| Aim / milestone | Revised target | Status as of Mar. 13 | Reason for the change |
| --- | --- | --- | --- |
| Aim 2.3: Implement selected beamforming or filtering kernels on PolarFire SoC and validate data movement | Mid Apr. | Pending | This makes the FPGA a primary technical milestone rather than a side demonstration. |
| Aim 2.4: Perform controlled testing with filters, attenuators, shielding aids, and FPGA/host comparisons | Mid Apr. | Pending | Needed to show whether FPGA offload materially improves the signal-processing path. |
| Aim 2.5: Measure suppression, coherence, latency, and runtime metrics across the Pi/FPGA processing path | Late Apr. | Pending | These metrics support the final report and quantify the value of the hybrid architecture. |
| Aim 3: Integrated hybrid demonstration | Early May | Upcoming | Aim 3 should show a clean end-to-end demo with visible FPGA contribution. |
| Aim 3.1: Demonstrate an FPGA-centered beamforming path with Raspberry Pi supervisory control | Late Apr. | Pending | Keeps the Pi important, but positions the FPGA as the major signal-processing engine. |
| Aim 3.2: Complete Raspberry Pi 5 to PolarFire SoC communication, configuration, and mode control | Late Apr. / Early May | Pending | Makes inter-platform control explicit without demoting the FPGA role. |
| Aim 3.3: Complete end-to-end demo with mode switching, logging, and recorded playback | Early May | Pending | Best visible end-to-end demonstration milestone. |
| Aim 3.4: Final validation run, figures, diagrams, and rehearsal | Early May | Pending | Protect time for documentation and demo polish. |
| Aim 3.5: Final report and presentation | Mid May | Pending | Final date remains unchanged. |

# Notes and assumptions

• This revision intentionally treats the wearable packaging concept as future commercialization context rather than the current semester’s main build target, while still keeping the FPGA-centered hybrid compute architecture as a major technical innovation within the present prototype.

• Where exact shipping status of some RF accessories was not explicitly confirmed in recent chats, the recommendation uses neutral labels such as 'in integration,' 'support item,' or 'optional/deferred' rather than overstating delivery status.

• If desired, this document can be converted into a final course-ready version after confirming the exact status of the PolarFire SoC board and the selected Taoglas antennas/cables.